## README
OPS Management System — Phase 1 Budget Model
Client budget: 300,000 EGP · Window: 10 Aug – 20 Nov 2026 · Team: BE + FE + DevOps
Purpose | Models the Phase 1 build against a fixed 300,000 EGP client budget, and states explicitly what that budget does and does not buy.
How to use it | Edit only the blue cells on the Assumptions sheet. Every other figure in the workbook is a formula and will recalculate.
Colour legend | BLUE text = input you can change · BLACK = calculated · GREEN = pulled from another sheet · YELLOW fill = assumption the client must confirm.
Balancing figure | Contingency is calculated as budget − labour − infrastructure. The grand total therefore always equals the budget exactly.
Headline | The budget funds ~8.3 person-months. That covers the Phase 1 scope in the technical proposal and nothing beyond it.
Key constraint | Bringing returns in-house costs ~3 person-weeks more than the E-stebdal integration it replaces. This was absorbed by moving the customer self-service portal to Phase 1b — which leaves Phase 1 with NO slack.
Implication | Any scope added after Sprint 0 must displace something else. See the Sensitivity sheet for the three levers available.
Scope change | Authentication and the Super Admin console were added after the first draft. They cost ~10 days inside Phase 1, paid for by moving three read-only surfaces to Phase 1b. See the Scope Changes sheet.
Sheets | Assumptions · Resource Allocation · Cost Breakdown · Infra and Tooling · Cash Flow · Scope Changes · Phase 1b and 2 · Sensitivity · ROI
Source | Figures derive from POC - Youssey Excelsheet.xlsx via scripts/extract_data.py and from published provider pricing (Aug 2026). Salary bands: Egyptian mid-level market, 18,000–42,000 EGP/month.

## Assumptions
Assumptions
Edit the BLUE cells only. Yellow fill = confirm with the client.
Assumption | Value | Unit | Basis / source
Client budget (Phase 1) | 300000 | EGP | Client-stated budget
Project start | 2026-08-10 | date | Sprint 0 begins
Code freeze / go-live | 2026-11-20 | date | 7 days before Black Friday (27 Nov 2026)
Black Friday | 2026-11-27 | date | Fixed external date
Project duration | 15 | weeks | 10 Aug – 20 Nov 2026
Weeks per month | 4.345 | weeks | 52 / 12
USD / EGP | 50.25 | EGP | Market rate, Aug 2026
EUR / EGP | 55 | EGP | Derived from USD/EGP at EURUSD ~1.09
Backend engineer — monthly cost | 34000 | EGP | Mid-level Egyptian market; the critical role
Frontend engineer — monthly cost | 27000 | EGP | Mid-level; Livewire/Blade profile, not React-only
DevOps engineer — monthly cost | 35000 | EGP | Mid-level; part-time allocation
Backend allocation | 1 | FTE | Full time across all sprints
Frontend allocation | 1 | FTE | Full time across all sprints
DevOps allocation | 0.4 | FTE | Front-loaded Sprint 1, then part time
Infrastructure months funded | 5 | months | Aug–Dec 2026, covering hypercare
Duration in months |  | months | Project duration ÷ weeks per month
Total person-months |  | person-mo | Sum of FTE allocations × duration in months
NOTE | Team model is IN-HOUSE SALARIED. Contractor rates typically run 1.3–1.8× and agency rates 2–3× these figures — at either, 300,000 EGP would not fund the Phase 1 scope. See the Sensitivity sheet.

## Resource Allocation
Resource Allocation by Sprint
FTE per role per sprint. Sprint effort is indicative; cost is driven by the Assumptions sheet.
Sprint | Dates | Primary focus | BE FTE | FE FTE | Ops FTE | Person-weeks
0 | 10–14 Aug | Discovery, credentials, schema, CS return-policy workshop | 1 | 0.5 | 1
1 | 17–28 Aug | Schema, RBAC, audit log, webhook inbox, Filament shell | 1 | 1 | 0.8
2 | 31 Aug–11 Sep | Shopify adapter, order ingestion, item-level splitting | 1 | 1 | 0.3
3 | 14–25 Sep | Bosta adapter, per-item AWB, status webhooks, flex-ship | 1 | 1 | 0.3
4 | 28 Sep–9 Oct | Financial engine: snapshots, ledger, 3 business models | 1 | 1 | 0.3
5 | 12–23 Oct | Returns & exchanges in-house, eligibility, reverse pickup | 1 | 1 | 0.4
6 | 26 Oct–6 Nov | Settlement, reconciliation, vendor portal, migration | 1 | 1 | 0.3
UAT | 9–20 Nov | UAT, parallel run, load test, cutover, hypercare prep | 1 | 1 | 0.6
Total person-weeks
Why DevOps is 0.4 FTE | Effort is front-loaded into Sprint 1 (environments, CI/CD, secrets, backups) and Sprint 5 (load test), with light steady-state work between. On a two-node deployment there is no Kubernetes or managed-broker work to justify a full-time role, and the hours are better spent on integrations — which is where the delivery risk actually sits.

## Cost Breakdown
Cost Breakdown — Phase 1
Contingency is the balancing figure, so the grand total always equals the client budget exactly.
Line item | Monthly (EGP) | FTE | Months | Total (EGP) | % of budget | Notes
LABOUR
Backend engineer | [5 empty] | Owns integrations, item splitting, financial engine, returns module
Frontend engineer | [5 empty] | Filament theming, dashboards, vendor portal, print layouts, Phase 1b portal
DevOps engineer | [5 empty] | Environments, CI/CD, monitoring, backups, load test, cutover
Labour subtotal
NON-LABOUR
Infrastructure and tooling | [5 empty] | Hosting, storage, CI, email, domain — itemised on the Infra sheet
Contingency | [5 empty] | BALANCING FIGURE = budget − labour − infrastructure. Covers integration surprises and the PDPL hosting fallback (see Sensitivity).
GRAND TOTAL
Check — total equals budget
Cost per person-month |  |  | Against the Egyptian mid-level band of 18,000–42,000 EGP/month, this sits mid-range — achievable, but not a rate that buys senior engineers.

## Infra and Tooling
Infrastructure and Tooling
Recommended: Hetzner Cloud CX line (EU) fronted by Cloudflare. See proposal §8.
Item | Spec | Native cost | Currency | EGP / month | Total (EGP) | Notes
Application node | CX43 — 8 vCPU / 16 GB | 15.99 | EUR |  |  | Ops console, vendor portal, workers, scheduler
Data node | CX33 — 4 vCPU / 8 GB | 8.49 | EUR |  |  | PostgreSQL 16 + Redis 7
Staging | CX23 — 2 vCPU / 4 GB | 5.49 | EUR |  |  | Full stack, sandbox integration credentials
Automated backups | 20% of server cost | 5.99 | EUR |  |  | Nightly snapshots, 30-day retention
Object storage | Storage Box 1 TB | 5 | EUR |  |  | AWB PDFs, payout proofs, off-site backups
Source control / CI | GitHub Team, 3 seats | 12 | USD |  |  | Actions free tier is sufficient
Transactional email | Amazon SES | 5 | USD |  |  | AWB labels and payout notifications to vendors
DNS / TLS / WAF / CDN | Cloudflare free tier | 0 | USD |  |  | Also provides DDoS protection
Error tracking | Sentry free tier | 0 | USD |  |  | 5k events/month covers this volume
Uptime monitoring | Uptime Kuma (self-hosted) | 0 | USD |  |  | Runs on the staging node
Domain registration | Annual, amortised | 600 | EGP |  |  | One-off within the project window
Sub-total
TOTAL (rounded up) | [5 empty] | Feeds the Cost Breakdown sheet
PDPL fallback | If legal counsel rejects EU hosting, Egyptian local hosting is estimated at 3,000–8,000 EGP/month — an increase of roughly 4,000 to 28,500 EGP across the project window, which must come from contingency. This is an indicative range, not a quote: obtaining two firm local quotes is a Sprint 0 action item.

## Cash Flow
Cash Flow by Month
Labour is spread by working weeks in each month. Infrastructure runs Aug–Dec.
Month | Weeks | Backend | Frontend | DevOps | Infrastructure | Monthly total | Cumulative
Aug 2026 | 3
Sep 2026 | 4.3
Oct 2026 | 4.4
Nov 2026 | 3.3
Dec 2026 | 0
Total
Contingency (undrawn) |  |  | Weeks are working weeks within each calendar month across the 10 Aug – 20 Nov window. December carries infrastructure only, for hypercare.
Committed + contingency
Reconciles to budget

## Scope Changes
Scope Changes — Authentication & Super Admin Console
Added after the first proposal draft. Phase 1 had no slack, so the cost is paid by displacement rather than absorbed silently.
ADDED TO PHASE 1 — cannot wait for peak week
Item | BE days | FE days | Ops days | Cost (EGP) | Why it cannot wait
Login, session policy, 2FA (Fortify) | 1.5 | 0 | 0 |  | Gates everything else — nothing can be role-scoped until it exists
User management + roles UI | 1 | 0.5 | 0 |  | Onboarding and offboarding staff during peak week
Permission matrix editor | 0.5 | 1 | 0 |  | Tuning a role without a deployment
Integrations console + credential rotation | 2 | 1 | 0 |  | Rotating a leaked key, checking webhook health
System health + dead-letter replay | 2 | 0.5 | 0 |  | Replaying a failed webhook at 2am on Black Friday
Added to Phase 1 |  |  |  |  | Total engineering days added inside the Phase 1 window
DISPLACED TO PHASE 1b — pays for the above
Item | BE days | FE days | Ops days | Cost (EGP) | Why it is safe to move
Basic vendor scorecard (§10) | 2 | 2 | 0 |  | A read model over data captured from day one — ships with full history
Executive dashboard (§11) | 1 | 2 | 0 |  | Same: a view over data already being collected, nothing lost retroactively
Vendor product submission (§8.1) | 2 | 2 | 0 |  | Vendors are onboarded through Ops today, so the manual path already exists
Displaced out of Phase 1 |  |  |  |  | Total engineering days moved to Phase 1b
NET EFFECT ON PHASE 1
Phase 1 budget impact
Stated plainly: the console is real work and Phase 1 had no slack, so something had to give. Displacing three read-only surfaces is the cheapest way to pay for it — they are views over data the system collects from day one, so they lose no history and simply arrive three weeks after go-live. The alternative, drawing on contingency, is modelled on the Sensitivity sheet and is not recommended while the PDPL hosting risk is open.

## Phase 1b and 2
Phase 1b and Phase 2 — Indicative Estimates
Not funded by the 300,000 EGP Phase 1 budget. Presented so the client can plan.
PHASE 1b — 23 Nov to 11 Dec 2026 (3 weeks)
Deliverable | BE days | FE days | Ops days | Cost (EGP) | Notes
Customer self-service returns portal | 4 | 8 | 1 |  | Order number + phone lookup, no account required
Returns analytics dashboard | 4 | 3 | 0 |  | By reason, vendor and stakeholder
E-stebdal parallel-run validation | 2 | 1 | 1 |  | Data parity check before January cutover
Super Admin: business rules engine UI | 3 | 2 | 0 |  | Phase 1 seeds these rules by migration
Super Admin: report builder + scheduling | 2 | 2 | 0 |  | Phase 1 ships a fixed set of built-in reports
Basic vendor scorecard (displaced from P1) | 2 | 2 | 0 |  | Read model - ships with full history
Executive dashboard (displaced from P1) | 1 | 2 | 0 |  | Read model - ships with full history
Vendor product submission (displaced from P1) | 2 | 2 | 0 |  | Vendors onboard through Ops in the interim
Phase 1b total |  |  |  |  | Assumes 21 working days per month
PHASE 2 — from January 2027
Deliverable | BE days | FE days | Ops days | Cost (EGP) | Requirement
Raw fabric inventory, BOM and forecasting | 15 | 6 | 0 |  | Req 7.2 — largest single Phase 2 item
Automated Paymob Send disbursement | 8 | 2 | 1 |  | Req 8.6 — human approval gate retained
Second courier adapter | 10 | 3 | 1 |  | Req 3.1 — per-item courier selection
Advanced vendor scorecard and penalties | 10 | 6 | 0 |  | Req 10
Executive BI dashboard | 8 | 6 | 0 |  | Req 11
Automated recall / win-back workflows | 7 | 4 | 0 |  | The §1.2 revenue case, automated
Phase 2 total |  |  |  |  | Excludes infrastructure
Phase 1 + 1b + 2 combined

## Sensitivity
Sensitivity Analysis
What the budget buys under different assumptions — and the three levers if the schedule slips.
BUDGET SENSITIVITY
Scenario | Budget (EGP) | Person-months | Δ vs plan | Scope consequence
Budget −20% |  |  |  | Phase 1 loses settlement automation AND the vendor scorecard. Order, shipping, returns and finance survive.
Budget −10% |  |  |  | Vendor scorecard deferred to Phase 1b. Everything else holds.
Plan as proposed |  |  |  | Full Phase 1 scope as defined in proposal §3.1. Zero slack.
Budget +10% |  |  |  | Restores ~3 weeks of slack — the single most valuable addition, given Phase 1 currently has none.
Budget +20% |  |  |  | Pulls the customer self-service returns portal back into Phase 1.
TEAM MODEL SENSITIVITY
Engagement model | Rate multiple | Person-months | Δ vs plan | Verdict
In-house salaried (assumed) | 1 |  |  | Phase 1 scope is achievable. This is the model the budget is built on.
Freelance / contractor | 1.5 |  |  | Buys roughly two thirds of the person-months. Phase 1 must shed settlement, scorecard and vendor portal v1.
Agency / software house | 2.5 |  |  | Buys under half. 300,000 EGP funds an MVP — Shopify sync, item splitting and shipping only. Returns and finance would not fit.
FUNDING THE ADMIN CONSOLE
Option | Cost (EGP) | Contingency left | Preference | Consequence
1. Displace 11 days of read-only UI | 0 |  | recommended | Vendor scorecard, executive dashboard and vendor product submission move to Phase 1b. All three are views over data captured from day one, so nothing is lost retroactively.
2. Draw on contingency |  |  | not while PDPL is open | Arithmetically it fits, but leaves too little against risk R1 - the PDPL hosting fallback alone could need up to 28,500 EGP.
3. Increase the budget |  |  | client's call | Roughly 16,000-20,000 EGP. Keeps every Phase 1 surface and restores the contingency.
SCHEDULE LEVERS
Lever | Cost (EGP) | Time recovered | Preference | Trade-off
1. Cut scope | 0 | ~2 weeks | Preferred | Defer settlement automation and vendor scorecard to Phase 1b. No cash cost.
2. Extend timeline | 0 | Unlimited | Second | Go live in December, after Black Friday. Removes all peak-week risk but forfeits a full peak season of benefit.
3. Add a 2nd backend engineer |  | ~3 weeks | Least effective | Only works if committed by mid-September. Later than that, onboarding drag exceeds the capacity added.

## ROI
Return on Investment
The case rests on recovered failed deliveries, not on data-entry savings. Proposal §1.2.
OPERATIONAL BASELINE — from the client's own data
Measure | Value | Unit | Source
Item rows analysed | 18341 | items | Copy of Orders, 1 Jan – 8 Aug 2026
Failed delivery (FD Allow Open Shipment) | 3743 | items | Final status column
Returned to origin (RTO) | 2359 | items | Final status column
Total failed items |  | items | FD + RTO
Average item value | 897 | EGP | GMV ÷ item rows
GMV that shipped and came back |  | EGP | Failed items × average value
Failed items actually worked (Send messages) | 1430 | items | Recall Status column
Recovered into new orders | 273 | items | Recall Status = Create new orders
Current recovery rate |  | % | Recovered ÷ worked
Failed items never worked |  | items | Total failed − worked
RECOVERY SCENARIOS — annualised
Scenario | Recovered items / yr | Recovered GMV / yr (EGP) | Assumption
Conservative |  |  | Half the current recovery rate applied to items never worked. Deliberately pessimistic: worked items were probably the most promising.
At parity |  |  | Current 19.1% recovery rate applied across all failed items, net of what is already recovered today.
PAYBACK
Phase 1 build cost |  |  | These are GMV figures, not profit. The platform realises commission and margin on recovered orders, not the full value. The point is the order of magnitude: even the conservative case returns more than twice the build cost in GMV within year one, and the recall queue is a permanent capability.
Recovered GMV, conservative case
Ratio — recovered GMV to build cost
RECURRING OFFSETS
E-stebdal subscription — monthly | 0 |  | CLIENT TO CONFIRM. Enter the current monthly subscription; the annual saving below will calculate. Retired at January 2027 cutover.
Annual saving from retiring E-stebdal
Manual data entry displaced |  | rows / working day | Across 32 columns with cross-system lookups per row. A real but soft saving — not counted in the payback figure above.